DOCUMENT 10

THE FAMILY COURT METRIC CATALOG

Risk Register

& Mitigation Matrix

Identified risks to the Metric Catalog and its Missouri pilot, with likelihood, severity, owner, and mitigation path.

PREPARED FOR

Board of Directors · Methodology Board · Funders

Missouri Pilot · Version 0.3 · 2026

A CoTrackPro Civic Publication

OVERVIEW

# Risk Register Structure

The Risk Register identifies known and anticipated risks to the Metric Catalog framework and the Missouri pilot. Each risk entry identifies likelihood (L/M/H), severity (L/M/H), the accountable owner, the primary mitigation strategy, and a contingency in case the mitigation fails. The Register is reviewed quarterly by the Methodology Board and revised at least annually.

Risks are grouped into four categories: Structural (threats to the framework's integrity), Operational (threats to pilot execution), Reputational (threats to stakeholder trust), and External (threats from outside the pilot's control).

CATEGORY I

# Structural Risks

Risks that could compromise the methodological or privacy integrity of the framework itself.

| RISK | L/S | OWNER | MITIGATION |
| --- | --- | --- | --- |
| Re-identification incident | L/H | Data Ethics Review | k-anonymity ≥ 10, differential privacy for n<30, quarterly adversarial testing, mandatory suspension on any detected incident. |
| Methodology capture by funder | M/H | Board Chair | 20% funder cap, public funder disclosure, rotating chair, no single funder in founding cohort > 15%. |
| Board composition drift | M/M | Nominating bodies | Staggered terms, constituency-specific nominations, annual composition audit. |
| Metric gaming by reporting entities | M/M | OSCA · Methodology Board | Independent validation sampling, methodology review for new gameable definitions, cross-source reconciliation. |

CATEGORY II

# Operational Risks

Risks to executing the pilot on time and within budget.

| RISK | L/S | OWNER | MITIGATION |
| --- | --- | --- | --- |
| OSCA MOU delays | M/H | Platform Partner | Early engagement, no-authority-required pilot design, parallel track conversations with each pilot circuit. |
| Pilot circuit non-participation | L/H | Platform Partner | Three-circuit redundancy, formal MOU with termination protection, presiding judge early involvement. |
| De-identification pipeline failure | L/H | CTO · Data Ethics | Four-gate pipeline, mandatory QA, independent audit before first publication, incident response runbook. |
| Key personnel loss | M/M | Executive Director | Documented operational procedures, board-level succession planning, cross-training on critical functions. |
| Budget shortfall | M/M | Executive Director · Board | Multi-funder stack, quarterly burn-rate monitoring, 10% contingency line, pre-approved scope-reduction plan. |

CATEGORY III

# Reputational Risks

Risks to stakeholder trust and the framework's continued credibility.

| RISK | L/S | OWNER | MITIGATION |
| --- | --- | --- | --- |
| DV advocate withdrawal | L/H | Board Chair · Data Ethics | MOCADSV early and continuous engagement, survivor safety as first review criterion, dedicated Board seat. |
| Fathers' rights rejection of "one-sided metrics" | M/H | Board Chair | Bilateral measurement by design, dedicated Board seat, methodology board representation. |
| Judicial independence challenge | M/H | Legal Counsel · OSCA | Judge-level data private by design, public materials explicitly exclude judicial ranking, judicial constituency on Board. |
| Media misinterpretation of aggregate data | H/M | Communications Lead | Methodology primer in every publication, dedicated press FAQ (Doc 18), rapid correction protocol. |
| Adversarial use in litigation | M/H | Legal Counsel | Evidentiary shield in draft RSMo § 452.317, amicus brief capacity for test cases, defensive posture documentation. |

CATEGORY IV

# External Risks

Risks from outside the pilot's direct control.

| RISK | L/S | OWNER | MITIGATION |
| --- | --- | --- | --- |
| Federal or state statutory change | L/M | Legal Counsel | Regulatory monitoring, rapid-response legal review, conservative disclosure posture under any ambiguity. |
| Competing framework adoption | M/L | Executive Director | Open-source methodology release, interoperability commitment, collaboration-first stance with any peer effort. |
| Political attack on transparency | L/H | Board Chair | Broad coalition of endorsers, non-partisan framing, fact-based response protocol. |
| Economic downturn reducing funding | M/M | Executive Director · Board | Diversified funding base, operational efficiency, clear scope-reduction decision tree. |

CONTINGENCY

# What Triggers Scope Reduction

If funding falls below sixty percent of planned budget for two consecutive quarters, or if a pilot circuit withdraws without being replaced within ninety days, the Board triggers a pre-approved scope-reduction sequence:

- Freeze new metric adoptions; maintain existing published metrics only.

- Reduce publication cadence from quarterly to semi-annual.

- Consolidate to two pilot circuits if three cannot be sustained.

- Pause Tier C metric publication while maintaining user-facing tools.

- If none of the above restores sustainability within twelve months, execute graceful wind-down per the Wind-Down Runbook (Appendix).