DOCUMENT 13

THE FAMILY COURT METRIC CATALOG

Budget Narrative

& Line-Item Schedule

Total 36-month pilot budget of $1,454,510 across five categories, with funding sources and assumptions.

PREPARED FOR

Funders · Board of Directors

Missouri Pilot · Version 0.3 · 2026

A CoTrackPro Civic Publication

SUMMARY

# Three-Year Budget

The Missouri pilot is budgeted at a total of $1,454,510 over thirty-six months. The budget is deliberately lean. It assumes one full-time executive director, one engineering lead (the current founder takes this role), two part-time contractors at different phases, one part-time methodology coordinator, and the cost of the Methodology Board and Data Ethics Review stipends.

| CATEGORY | YEAR 1 | YEAR 2 | YEAR 3 | TOTAL |
| --- | --- | --- | --- | --- |
| Personnel | $318,000 | $331,000 | $345,000 | $994,000 |
| Board & Reviews | $42,000 | $44,000 | $46,000 | $132,000 |
| Infrastructure & Ops | $46,500 | $48,200 | $50,000 | $144,700 |
| Academic Partnerships | $45,000 | $45,000 | $45,000 | $135,000 |
| Contingency (10%) | $15,810 | $14,970 | $18,030 | $48,810 |
| TOTAL | $467,310 | $483,170 | $504,030 | $1,454,510 |

PERSONNEL

# Personnel Detail

Personnel costs reflect St. Louis/Missouri market rates for nonprofit civic tech. All positions are US-based, employed through the Platform Partner entity or a fiscal sponsor.

| ROLE | FTE | YEAR 1 | YEAR 2 | YEAR 3 |
| --- | --- | --- | --- | --- |
| Executive Director | 1.0 | $130,000 | $135,000 | $141,000 |
| Engineering Lead (Founder) | 1.0 | $95,000 | $99,000 | $103,000 |
| Methodology Coordinator | 0.5 | $43,000 | $45,000 | $47,000 |
| Research/Data Analyst | 0.5 | $35,000 | $37,000 | $39,000 |
| Contract (privacy audit) | 0.2 | $15,000 | $15,000 | $15,000 |

BOARD & REVIEWS

# Methodology Board and Data Ethics Review

Methodology Board members are not compensated for meeting attendance, but receive modest per-meeting honoraria ($500 per quarterly meeting) to enable participation by practitioners and lived-experience members who could not otherwise donate the time. Data Ethics Review members are compensated at $2,000 per completed review to support timely independent analysis.

- Methodology Board honoraria (11 members × 4 meetings × $500): $22,000 per year.

- Data Ethics Review honoraria (5 members × approx. 2 reviews each per year × $2,000): $20,000 per year.

INFRASTRUCTURE & OPS

# Technical and Operational Costs

- AWS infrastructure (DynamoDB, Lambda, API Gateway, S3, Cognito, CloudWatch, SSM): $14,000-18,000 per year depending on usage. Estimated at $15,000 Year 1 growing to $17,500 Year 3.

- Third-party tools (observability, incident response, legal/compliance): $8,000-10,000 per year.

- Independent security audit (annual): $12,000.

- Office and meeting costs (modest): $3,000 per year.

- Insurance (cyber liability $2M, E&O): $8,000 per year.

ACADEMIC PARTNERSHIPS

# Research Collaboration Budget

Each of the three law-school partners (Wash U, Mizzou, Missouri State) receives $15,000 per year for one semester of graduate student research assistance, methodology consultation, and IRB costs. This is not a grant; it is a service contract that requires deliverables: methodology contributions, internal validation studies, and academic publications.

FUNDING SOURCES

# Blended Funding Stack

The pilot is funded from a blended stack that caps any single funder at 20% of the total budget. This cap is enforced regardless of funder category.

| SOURCE CATEGORY | TARGET % | AMOUNT | STATUS |
| --- | --- | --- | --- |
| Philanthropy (access-to-justice funders) | 40% | $581,804 | Active cultivation |
| Academic institutional partnerships | 15% | $218,177 | Contracted at partner level |
| Individual and community donors | 15% | $218,177 | Ongoing |
| CoTrackPro subscription revenue (modest contribution) | 10% | $145,451 | Existing revenue stream |
| State (future statutory authorization, after pilot) | 0-20% | $0-290,902 | Not in Phase 1 |

ASSUMPTIONS

# What This Budget Assumes

- One executive director hired within three months of funding secured.

- No additional staff beyond those listed, for the duration of the pilot.

- Pilot circuits do not require reimbursement for their participation (MOU structure assumes this).

- AWS infrastructure remains within AWS Activate credits for the first six months.

- Academic partners provide in-kind contribution (faculty time, IRB infrastructure) in addition to the contracted $15k per year.

- No litigation expenses budgeted; any test cases would require separate supplemental funding.

- Currency assumption: all figures in 2026 US dollars; no inflation adjustment applied to Year 2 or Year 3 beyond 3% general escalation.

- Contingency of 10% held in reserve for unanticipated needs; annual review determines release.

WHAT HAPPENS AT YEAR 3

# Sustainability Planning

The pilot does NOT assume continued grant funding beyond Year 3. Two scenarios are contemplated:

- Scenario A: Pilot demonstrates sufficient impact to attract statutory funding, either as a line item in the OSCA budget or through a dedicated civic-tech appropriation. Target: 20% of post-pilot budget from state source.

- Scenario B: Sustained philanthropic interest + growing CoTrackPro subscription revenue + academic contract revenue covers the ongoing costs of maintaining published metrics without new-metric development.

A formal sustainability review occurs at Month 24 of the pilot. If neither scenario is tracking by that point, the Wind-Down Runbook activates to enable graceful transition of the published Catalog to another host organization or to public-domain archive status.